## Summary for Emergency Estimate
Summary of Cost Estimate of Emergency
Agreement Ref. RMF/2020- 2021/26
| Initial Amount | Revised Amount
Spots in Nyanza | 27820195.5601 | 30894495.11
Tax (15%) | 4909446.2753 | 5451969.7253
SubTot.01 | 32729641.8355 | 36346464.8353
Spots in Nyaruguru | 278510337.844 | 336538292.68
Tax (15%) | 49148883.1489 | 59389110.4729
SubTot.02 | 327659220.9929 | 395927403.1529
Grand Total | 360388862.8284 | 432273867.9882
Additional Amount |  | 71885005.1598
Proposed Additional Funds (%) |  | 19.95%

## Nyaruguru BoQ Rev.01
BoQ for damaged different road spots in Nyaruguru District
N° | DESCRIPTION | Unit | Qty Ref. | Qty Rev01 | Rate | Init. Amount | Amount Rev01
1 | Site installation
1.1 | Site Installation and Withdraw | LS | 1 | 1 | 18000000 | 18000000 | 18000000
1.2 | Topography (Before, During and After Works) | LS | 1 | 1 | 2500000 | 2500000 | 2500000
| Sub/Total |  |  |  |  | 20500000 | 20500000
B2 | Akanyaru Bridge_Muganza_Giswi_Kivu TP
B2.1 | Removal of landslides, debris and sediments_ including hauling and final Disposal (CH 0+000 to CH 13+100) | m3 | 1122 | 0 | 3500 | 3927000 | 0
B2.2 | Ordinary cutting hauling and final Disposal (CH 0+000 to CH 13+100) | m3 | 990 | 0 | 5128 | 5076720 | 0
B2.3 | Supply and Installation of the Pipe culvert Ø100 (CH 0+000 to CH 13+100) | m | 8 | 0 | 250000 | 2000000 | 0
B2.4 | Construction of the outlet (Stone Masonry Drain / Gabions) (CH 0+000 to CH 13+100) | m3 | 17.1 | 0 | 80146 | 1370496.6 | 0
B2.5 | Plain Concrete | m3 | 0.54 | 0 | 250000 | 135000 | 0
B2.6 | RCC concrete | m3 | 5.1 | 0 | 450000 | 2295000 | 0
B2.7 | Removal of landslides, debris and sediments_ including hauling and final Disposal (CH 13+100 to CH 15+500) | m3 | 2916 | 0 | 3500 | 10206000 | 0
| Sub/Total |  |  |  |  | 25010220
B3 | Kivu TP_ Nyabimata_ Bigugu
B3.1 | Removal of landslides, debris and sediments_ including hauling and final Disposal (CH 15+500 to CH 26+000) | m3 | 2624.4 | 0 | 3500 | 9185400 | 0
B3.2 | Construction of Stone Masonry drain | m3 | 28.5 | 0 | 75074 | 2139609 | 0
B3.3 | Supply and Installation of the Pipe culvert Ø100 | m | 14 | 0 | 250000 | 3500000 | 0
B3.4 | Construction of Stone Masonry drain | m3 | 45.6 | 0 | 75074 | 3423374.4 | 0
B3.5 | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | 2430 | 0 | 3500 | 8505000 | 0
B3.6 | Construction of Stone Masonry drain | m3 | 513 | 0 | 75074 | 38512962 | 0
B3.7 | Restoration of the road wearing course with selected materials | m3 | 1260 | 0 | 13989 | 17626140 | 0
B3.8 | Supply and Installation of the Pipe culvert Ø80 (Double) | m | 14 | 0 | 220000 | 3080000 | 0
B3.9 | Construction of Stone Masonry drain (Outlet)/ Gabions | m3 | 45.6 | 0 | 75074 | 3423374.4 | 0
B3.10 | Plain Concrete | m3 | 1.44 | 0 | 250000 | 360000 | 0
B3.11 | RCC concrete | m3 | 13.6 | 0 | 450000 | 6120000 | 0
B3.12 | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | 1944 | 0 | 3500 | 6804000 | 0
B3.13 | Restoration of the road wearing course with selected materials | m3 | 1400 | 0 | 13989 | 19584600 | 0
B3.14 | Construction of Stone Masonry drain | m3 | 570 | 0 | 75074 | 42792180 | 0
B3.15 | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | 1166.4 | 0 | 3500 | 4082400 | 0
B3.16 | Supply and Installation of the Pipe culvert Ø100 | m | 8 | 0 | 250000 | 2000000 | 0
B3.17 | Ordinary cutting (to extend the CW_ width) hauling and final Disposal | m3 | 2400 | 0 | 5128 | 12307200 | 0
B3.18 | Construction of the outlet (Stone Masonry Drain/ Gabions) | m3 | 28.5 | 0 | 75074 | 2139609 | 0
B3.19 | Supply and Construction of Gabions | m3 | 5 | 0 | 80146 | 400730 | 0
B3.20 | Supply and installation of beacons | m3 | 12 | 0 | 25000 | 300000 | 0
B3.21 | Wood lumber (squired) | m | 15 | 0 | 50000 | 750000 | 0
B3.22 | Construction of Stone Masonry (Head wall, retaining wall) | m3 | 9 | 0 | 75074 | 675666 | 0
| Sub/Total |  |  |  |  | 187711803
B4 | Nyabimata_ Muganza
B4.1 | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | 4500 | 6257.92 | 3500 | 15750000 | 21902720
B4.2 | Restoration of the road wearing course with selected materials | m3 | 420 | 2800 | 13989 | 5875380 | 39169200
B4.3 | Supply and Installation of the Pipe culvert Ø100 | m | 0 | 40 | 250000 | 0 | 10000000
B4.4 | Construction of the outlet (Stone Masonry Drain/ Gabions) | m3 | 0 | 189.2 | 75074 | 0 | 14204000.8
B4.5 | Construction of Stone Masonry drain (open canal) | m3 | 0 | 134.32 | 75074 | 0 | 10083939.68
B4.6 | Plain concrete | m3 | 0 | 41.54 | 250000 | 0 | 10385000
B4.7 | RCC concrete | m3 | 0 | 17.33 | 450000 | 0 | 7798500
B4.8 | Ordinary cutting (to extend the CW_ width) hauling and final Disposal | m3 | 0 | 1434.48 | 5128 | 0 | 7356013.44
B4.9 | Stone masonry wall on the bridges | m3 | 0 | 90 | 75074 | 0 | 6756660
B4.10 | Stone masonry wall | m3 | 0 | 78.56 | 75074 | 0 | 5897813.44
| Sub/Total |  |  |  |  | 21625380 | 133553847.36
B5 | Giswi- Uwinteko- Shili
B5.1 | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | 980 | 3252.88 | 3500 | 3430000 | 11385080
B5.2 | Restoration of the road wearing course with selected materials | m3 | 63 | 2100 | 13989 | 881307 | 29376900
B5.3 | Supply and Installation of the Pipe culvert Ø100 | m | 0 | 18 | 250000 | 0 | 4500000
B5.4 | Construction of the outlet (Stone Masonry Drain/ Gabions) | m3 | 0 | 107.8 | 75074 | 0 | 8092977.2
B5.5 | Plain Concrete | m3 | 0 | 14.7 | 250000 | 0 | 3675000
B5.7 | Ordinary cutting (to extend the CW_ width) hauling and final Disposal | m3 | 0 | 2633 | 5128 | 0 | 13502024
| Sub/Total |  |  |  |  | 4311307 | 70531981.2
B6 | Kibeho-Kivu TP
B6.1 | Supply and Installation of the Pipe culvert Ø100 | m | 16 | 19 | 250000 | 4000000 | 4750000
B6.2 | Construction of the outlet (Stone Masonry Drain/ Gabions) | m3 | 14.25 | 189.2 | 75074 | 1069799 | 14204000.8
B6.3 | Plain Concrete | m3 | 0.45 | 26.25 | 250000 | 112500 | 6562500
B6.4 | RCC concrete | m3 | 4.25 | 4.5 | 450000 | 1912500 | 2025000
B6.5 | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | 1512 | 3059.47 | 3500 | 5292000 | 10708145
B6.6 | Restoration of the road wearing course with selected materials | m3 | 70 | 70 | 13989 | 979230 | 979230
B6.7 | Ordinary cutting (to extend the CW_ width) hauling and final Disposal | m3 | 750 | 7622.94 | 5128 | 3846000 | 39090436.32
B6.8 | Construction of Stone Masonry drain (stone masonry/Gabion) | m3 | 28.5 | 448 | 75074 | 2139599 | 33633152
| Sub/Total |  |  |  |  | 19351628 | 111952464.12 | Spots in Nyanza | 27820195.5601 |  | 30894495.11
[8 empty] | Tax Nyanza | 4909446.2753 |  | 5451969.7253
| Total |  |  |  |  | 278510338 | 336538292.68 | Total | 32729641.8355 |  | 36346464.8353
| Withhold Tax (15%) |  |  |  |  | 49148883.1765 | 59389110.4729
| General Total |  |  |  |  | 327659221.1765 | 395927403.1529 | Spots in Nyaruguru | 278510337.844 |  | 336538292.68
[8 empty] | Tax Nyarug | 49148883.1489 |  | 59389110.4729
[6 empty] | Diff contract | 68268181.9765 | Total | 327659220.9929 |  | 395927403.1529
[6 empty] | % | 20.84% |  |  |  | ToT Tax Incl.
[6 empty] | Contract | 360388862.8284 | Grand Total | 360388862.8284 |  | 432273867.9882
[8 empty] | 20% | 72077772.5657
71885005.1598
[10 empty] | Add | 19.95%
[10 empty] | Diff | 192767.4058

## Nyaruguru BoQ Details
|  | BoQ for damaged different road spots in Nyaruguru District |  |  | Calculation Details for Revised BoQ
| 1 | Site installation | Unit | Qty Ref. | Rate | Length | Width | Thickness | Volume | Qty Rev01 | Amount Rev01
| 1.1 | Site Installation and Withdraw | LS | 1 | 18000000 |  |  |  |  | 1 | 18000000
| 1.2 | Topography (Before, During and After Works) | LS | 1 | 2500000 |  |  |  |  | 1 | 2500000
|  | Sub/Total | [8 empty] | 20500000
| B4 | Nyabimata_ Muganza
| B4.1 | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | 4500 | 3500 |  |  |  |  | 6257.92 | 21902720
| B4.2 | Restoration of the road wearing course with selected materials | m3 | 420 | 13989 |  |  |  |  | 2800 | 39169200
| B4.3 | Supply and Installation of the Pipe culvert Ø100 | m |  | 250000 |  |  |  |  | 40 | 10000000
| B4.4 | Construction of the outlet (Stone Masonry Drain/ Gabions) | m3 |  | 75074 |  |  |  |  | 189.2 | 14204000.8
| B4.5 | Construction of Stone Masonry drain (open canal) | m3 |  | 75074 |  |  |  |  | 134.32 | 10083939.68
| B4.6 | Plain concrete | m3 |  | 250000 |  |  |  |  | 41.54 | 10385000
| B4.7 | RCC concrete | m3 |  | 450000 |  |  |  |  | 17.33 | 7798500
| B4.8 | Ordinary cutting (to extend the CW_ width) hauling and final Disposal | m3 |  | 5128 |  |  |  |  | 1434.48 | 7356013.44
| B4.9 | Stone masonry Drain (wall on the bridges) | m3 |  | 75074 |  |  |  |  | 90 | 6756660
| B4.10 | Stone masonry drain | m3 |  | 75074 |  |  |  |  | 78.56 | 5897813.44
|  | Sub/Total | [8 empty] | 133553847.36
PK1+270 |  | Supply and Installation of the Pipe culvert Ø100 | m |  |  | 10
PK4+400 |  | Supply and Installation of the Pipe culvert Ø100 | m |  |  | 9
PK5+700 |  | Supply and Installation of the Pipe culvert Ø100 | m |  |  | 12
PK6+345 |  | Supply and Installation of the Pipe culvert Ø100 | m |  |  | 9
PK1+270 |  | Construction of the outlet (Stone Masonry Drain/ Gabions) | m3 |  |  | 20 | 5.5 | 0.4 | 44
PK1+270 |  | Plain Concrete in outlet drain | m3 |  |  | 20 | 2 | 0.15 | 6
PK5+700 |  | Construction of the outlet (Stone Masonry Drain/ Gabions) | m3 |  |  | 22 | 5.5 | 0.4 | 48.4
PK5+700 |  | Plain Concrete in outlet drain | m3 |  |  | 22 | 2 | 0.15 | 6.6
PK6+345 |  | Construction of the outlet (Stone Masonry Drain/ Gabions) | m3 |  |  | 23 | 5.5 | 0.4 | 50.6
PK2+200 |  | RCC concrete in bridge Giswi | m3 |  |  | 18 | 1 | 0.5 | 9
PK6+345 |  | Plain Concrete in outlet drain | m3 |  |  | 23 | 2 | 0.15 | 6.9
PK4+400 |  | Construction of the outlet (Stone Masonry Drain/ Gabions) | m3 |  |  | 21 | 5.5 | 0.4 | 46.2
PK4+400 |  | Plain Concrete in outlet drain | m3 |  |  | 21 | 2 | 0.15 | 6.3
PK2+200 |  | RCC concrete (dallet) on top of water canal | m3 |  |  | 7 | 1.2 | 0.2 | 1.68
PK1+900 to PK2+400 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 2274.8
PK3+000 to PK3+210 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 653.24
PK3+400 to PK4+300 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | [6 empty] | 841.13
PK4+700 to PK5+600 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 1689.96
PK5+900 to PK6+800 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | [6 empty] | 798.79
PK0+000 |  | Restoration of the road wearing course with selected materials | m3 | [5 empty] | 2800
PK3+000 to PK4+450 |  | Ordinary cutting (to extend the CW_ width) hauling and final Disposal | m3 | [5 empty] | 938.08
PK2+200 |  | Construction of Stone Masonry drain | m3 |  |  | 21 | 1.2 | 0.3 | 7.56
PK1+974 |  | Ordinary cutting (to extend the CW_ width) hauling and final Disposal | m3 | [5 empty] | 496.4
PK2+200 |  | Stone masonry wall on the bridge (wing wall) in Giswi bridge | m3 |  |  | 8 | 6 | 0.75 | 36
PK3+240 |  | Plain concrete | m3 |  |  | 7 | 1 | 0.05 | 0.35
PK3+240 |  | RCC Concrete | m3 |  |  | 7 | 1 | 0.4 | 2.8
PK3+240 |  | Stone masonry wall (retaining wall) | m3 |  |  | 7 | 4 | 0.5 | 14
PK3+240 |  | Rehabilitation of wing wall in stone masonry in Migendo bridge | m3 |  |  | 8 | 9 | 0.75 | 54
PK5+000 |  | RCC Concrete in construction of stone masonry drain | m3 |  |  | 15.4 | 1 | 0.25 | 3.85
PK5+000 |  | Construction of stone masonry drain | m3 |  |  | 15.4 | 0.6 | 5 | 46.2
PK6+800 |  | Construction of Stone Masonry drain | m3 |  |  | 30 | 1.2 | 0.3 | 10.8
PK6+800 |  | Plain concrete in drain canal | m3 |  |  | 30 | 0.5 | 0.15 | 2.25
PK6+800 |  | construction of stone masonry Open canal (open canal) | m3 |  |  | 73 | 4.6 | 0.4 | 134.32
PK6+800 |  | Plain concrete in open canal | m3 |  |  | 73 | 1.2 | 0.15 | 13.14
| B5 | Giswi- Uwinteko- Shili
| B5.1 | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | 980 | 3500 |  |  |  |  | 3252.88 | 11385080
| B5.2 | Restoration of the road wearing course with selected materials | m3 | 63 | 13989 |  |  |  |  | 2100 | 29376900
| B5.3 | Supply and Installation of the Pipe culvert Ø100 | m |  | 250000 |  |  |  |  | 18 | 4500000
| B5.4 | Construction of the outlet (Stone Masonry Drain/ Gabions) | m3 |  | 75074 |  |  |  |  | 107.8 | 8092977.2
| B5.6 | Plain Concrete | m3 |  | 250000 |  |  |  |  | 14.7 | 3675000
| B5.7 | Ordinary cutting (to extend the CW_ width) hauling and final Disposal | m3 |  | 5128 |  |  |  |  | 2633 | 13502024
|  | Sub/Total | [8 empty] | 70531981.2
PK0+600 to PK1+300 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 655.3 |  |  | 219.3
PK4+800 to PK5+600 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 376.98
PK0+000 |  | Restoration of the road wearing course with selected materials | m3 | [5 empty] | 2100
PK1+974 |  | Supply and Installation of the Pipe culvert Ø100 | m |  |  | 8
PK3+650 |  | Supply and Installation of the Pipe culvert Ø100 | m |  |  | 8
PK1+974 |  | Construction of the outlet (Stone Masonry Drain/ Gabions) | m3 |  |  | 26 | 5.5 | 0.4 | 57.2
PK3+650 |  | Construction of the outlet (Stone Masonry Drain/ Gabions) | m3 |  |  | 23 | 5.5 | 0.4 | 50.6
PK1+974 |  | Plain Concrete in outlet drain | m3 |  |  | 26 | 2 | 0.15 | 7.8
PK3+650 |  | Plain Concrete in outlet drain | m3 |  |  | 23 | 2 | 0.15 | 6.9
PK0+050 to PK0+400 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 860.3
PK4+700 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 519.92
PK1+900 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 840.38
PK2+300 to PK3+200 |  | Ordinary cutting (to extend the CW_ width) hauling and final Disposal | m3 | [5 empty] | 2633 |  |  | 2108
| B6 | KiVU - KIBEHO
| B6.1 | Supply and Installation of the Pipe culvert Ø100 | m | 16 | 250000 |  |  |  |  | 19 | 4750000
| B6.2 | Construction of the outlet (Stone Masonry Drain/ Gabions) | m3 | 14.25 | 75074 |  |  |  |  | 189.2 | 14204000.8
| B6.3 | Plain Concrete | m3 | 0.45 | 250000 |  |  |  |  | 26.25 | 6562500
| B6.4 | RCC concrete | m3 | 4.25 | 450000 |  |  |  |  | 4.5 | 2025000
| B6.5 | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | 1512 | 3500 |  |  |  |  | 3059.47 | 10708145
| B6.6 | Restoration of the road wearing course with selected materials | m3 | 70 | 13989 |  |  |  |  | 70 | 979230
| B6.7 | Ordinary cutting (to extend the CW_ width) hauling and final Disposal | m3 | 750 | 5128 |  |  |  |  | 7622.94 | 39090436.32
| B6.8 | Construction of Stone Masonry drain (stone masonry/Gabion) | m3 | 28.5 | 75074 |  |  |  |  | 448 | 33633152
|  | Sub/Total | [8 empty] | 111952464.12
PK0+000 |  | Restoration of the road wearing course with selected materials | m3 | [5 empty] | 70
PK12+800 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 167.95
PK12+100 to PK12+250 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 399.09
PK11+800 to PK11+900 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 301.45
PK10+800 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 188.21
PK9+200 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 876.3
PK7+750 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 432.1
PK7+300 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 202.09
PK6+300 to PK5+600 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 317.11
PK4+000 to PK3+900 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 61.3
PK2+300 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 23.67
PK 0+100 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 90.2
PK8+200 |  | Ordinary cutting (to extend the CW_ width) hauling and final Disposal | m3 | [5 empty] | 1891.9
PK7+550 |  | Ordinary cutting (to extend the CW_ width) hauling and final Disposal | m3 | [5 empty] | 5731.04
PK13+650 |  | Supply and Installation of the Pipe culvert Ø100 | m |  |  | 8
PK7+550 |  | Supply and Installation of the Pipe culvert Ø100 | m |  |  | 11
PK13+650 |  | Construction of the outlet (Stone Masonry Drain/ Gabions) | m3 |  |  | 39 | 5.5 | 0.4 | 85.8
PK7+550 |  | Construction of the outlet (Stone Masonry Drain/ Gabions) | m3 |  |  | 47 | 5.5 | 0.4 | 103.4
PK11+205 |  | Plain Concrete | m3 |  |  | 9 | 1 | 0.05 | 0.45
PK13+650 |  | Plain Concrete in outlet drain | m3 |  |  | 39 | 2 | 0.15 | 11.7
PK7+550 |  | Plain Concrete in outlet drain | m3 |  |  | 47 | 2 | 0.15 | 14.1
PK11+205 |  | RCC concrete | m3 |  |  | 9 | 1 | 0.5 | 4.5
PK13+550 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 1504.62
PK8+00 to PK11+260 |  | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | [5 empty] | 1370.38
PK13+724 toPK13+540 |  | Construction of Stone Masonry drain (Gabion) | m3 |  |  | 38 | 1 | 8 | 304
PK11+205 |  | Construction of Stone Masonry drain (Gabion) | m3 |  |  | 9.6 | 1 | 3 | 28.8
PK12+300 |  | Construction of stone Masonry drain | m3 |  |  | 64 | 0.6 | 3 | 115.2
|  | Total | [8 empty] | 336538292.68
|  | Withhold Tax (15%) | [8 empty] | 59389110.4729
|  | General Total | [8 empty] | 395927403.1529

## Nyanza BoQ Rev.01
BoQ for damaged road spots on NR6 in Nyanza District
N° | DESCRIPTION | Unit | Qty Ref. | Qty Rev01 | Rate | Init. Amount | Amount Rev01 | Qty Exec. | Amount Exec. | Progr.%
1 | Site installation
1.1 | Site Installation and Withdraw | LS | 1 | 1 | 3500000 | 3500000 | 3500000 |  | 0
1.2 | Topography (Before, During and After Works) | LS | 1 | 1 | 500000 | 500000 | 500000 |  | 0
| Sub/Total |  |  |  |  | 4000000 | 4000000 |  | 0
A2 | Preparatory Works
A2.1 | Clearing, Cleaning and stripping topsoil | m2 | 280 | 280 | 1417.0915 | 396785.62 | 396785.62 |  | 0
A2.2 | Demolition & removal of damaged head wall and wing wall protection in gabions / stone masonry | m3 | 70.5 | 92.5 | 5000 | 352500 | 462500 |  | 0
A2.3 | Excavation and removal of failed material (layers) from the road section; drain and culverts (outlet & inlet) | m3 | 356 | 399 | 5128 | 1825568 | 2046072 |  | 0
| Sub/Total |  |  |  |  | 2574853.62 | 2905357.62 |  | 0
A3 | Pipe Culvert and road section
A3.1 | Construction of a new head and wing walls in stone masonry | m3 | 33 | 83.85 | 75073.6429 | 2477430.2149 | 6294924.9551 |  | 0
A3.2 | Back fill with selected materials to restore the affected road layers | m3 | 306 | 358.1827 | 13989 | 4280634 | 5010617.9 |  | 0
A3.3 | Supply and installation of pipe culverts Ø80 | m | 8 | 8 | 220000 | 1760000 | 1760000 |  | 0
A3.4 | Supply and installation of pipe culverts Ø100 | m | 8 | 8 | 250000 | 2000000 | 2000000 |  | 0
A3.5 | Onbed RCC slab to protect the outlet of the culvert | m3 | 4.725 | 2.5 | 450000 | 2126250 | 1125000 |  | 0
A3.6 | Supply and installation of gabions | m3 | 4 | 4 | 80146.1863 | 320584.7452 | 320584.7452 |  | 0
A3.7 | Plain concrete | m3 | 3 | 7.65 | 250000 | 750000 | 1912500 |  | 0
A3.8 | Reinforced concrere (RCC) | m3 | 0.7 | 0 | 450000 | 315000 | 0 |  | 0
A3.9 | Stone masonry wall | m3 | 5.1 | 15.44 | 75073.6429 | 382875.5787 | 1159137.046 |  | 0
| Sub/Total |  |  |  |  | 14412774.5388 | 19582764.6463 |  | 0
A4 | Drain
A4.1 | Construction of stone masonry drain and manhole | m3 | 75.6 | 45.8 | 75073.6429 | 5675567.4013 | 3438372.8437 |  | 0
A4.2 | Installation of Drift | m | 9 | 0 | 21000 | 189000 | 0 |  | 0
A4.3 | Readjust the drain to the main outlet through existing (timber) culvert | m | 8 | 8 | 21000 | 168000 | 168000 |  | 0
| Sub/Total |  |  |  |  | 6032567.4013 | 3606372.8437 |  | 0
A5 | Safety features
A5.1 | RCC_Beacons | Pce | 32 | 32 | 25000 | 800000 | 800000 |  | 0
| Sub/Total |  |  |  |  | 800000 | 800000 |  | 0
| Total |  |  |  |  | 27820195.5601 | 30894495.11 |  | 0
| Withhold Tax (15%) |  |  |  |  | 4909446.2753 | 5451969.7253 |  | 0
| General Total |  |  |  |  | 32729641.8355 | 36346464.8353 |  | 0