## SUMMARY
RWANDA DEFENCE FORCE
ENGINEER BRIGADE
TEL : 0783108220
E-mail: Rdf-engrbde@minadef.gov.rw
Mar - 21
SUMMARY PROGRESS FOR EMERGENCY WORKS FOR DIFFERENT SPOTS AT NYANZA AND NYARUGURU ROAD
N° | DESCRIPTION OF WORKS | CONTR.AMOUNT | EXEC. AMOUNT | PROGRESS
1 | NYANZA | 27820195.5601 | 23594360.8149 | 84.81%
2 | NYARUGURU | 278510337.844 | 52327398.2329 | 18.79%
| TOTAL (WITHOLDING TAX EXCLUSIVE) | 306330533.4041 | 75921759.0478 | 24.78%
| TOTAL WITHOLDING TAX 15% | 54058329.4243 | 13397957.479
| GRAND TOTAL (WITHOLDING TAX INCLUSIVE) | 360388862.8284 | 89319716.5268

## NYARU RRVISED
Progress for Emergency maintenance works for damaged sections on different roads in Nyaruguru District.
S/No | ITEM DESCRIPTION | UNIT | QTY | RATE | AMOUNT | EXEC QTY | EXEC AMT | PROG%
1 | Site installation
1.1 | Site Installation and Withdraw | LS | 1 | 18000000 | 18000000 | 0.8 | 14400000 | 80%
1.2 | Topography (Before, During and After Works) | LS | 1 | 2500000 | 2500000 | 0.5 | 1250000 | 50%
| S/total |  |  |  | 20500000 |  | 15650000
2 | Akanyaru Bridge_Muganza_Giswi_Kivu TP
2.1 | Removal of landslides, debris and sediments_ including hauling and final Disposal (CH 0+000 to CH 13+100) | m3 | 1122 | 3500 | 3927000 | 0 | 0 | 0%
2.2 | Ordinary cutting hauling and final Disposal (CH 0+000 to CH 13+100) | m3 | 990 | 5128 | 5076720 | 0 | 0 | 0%
2.3 | Supply and Installation of the Pipe culvert ɸ100 (CH 0+000 to CH 13+100) | m | 8 | 250000 | 2000000 | 0 | 0 | 0%
2.4 | Construction of the outlet (Stone Masonry Drain / Gabions) (CH 0+000 to CH 13+100) | m3 | 17.1 | 80146.1863 | 1370499.7859 | 0 | 0 | 0%
2.5 | Plain Concrete | m3 | 0.54 | 250000 | 135000 | 0 | 0 | 0%
2.6 | RCC concrete | m3 | 5.1 | 450000 | 2295000 | 0 | 0 | 0%
2.7 | Removal of landslides, debris and sediments_ including hauling and final Disposal (CH 13+100 to CH 15+500) | m3 | 2916 | 3500 | 10206000 | 0 | 0 | 0%
| S/total |  |  |  | 25010219.7859
3 | Kivu TP_ Nyabimata_ Bigugu
3.1 | Removal of landslides, debris and sediments_ including hauling and final Disposal (CH 15+500 to CH 26+000) | m3 | 2624.4 | 3500 | 9185400 | 0 | 0 | 0%
3.2 | Construction of Stone Masonry drain | m3 | 28.5 | 75073.6429 | 2139598.8219 | 0 | 0 | 0%
3.3 | Supply and Installation of the Pipe culvert ɸ 100 | m | 14 | 250000 | 3500000 | 0 | 0 | 0%
3.4 | Construction of Stone Masonry drain | m3 | 45.6 | 75073.6429 | 3423358.1151 | 0 | 0 | 0%
3.5 | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | 2430 | 3500 | 8505000 | 0 | 0 | 0%
3.6 | Construction of Stone Masonry drain | m3 | 513 | 75073.6429 | 38512778.7949 | 0 | 0 | 0%
3.7 | Restoration of the road wearing course with selected materials | m3 | 1260 | 13989 | 17626140 | 0 | 0 | 0%
3.8 | Supply and Installation of the Pipe culvert ɸ 80 (Double) | m | 14 | 220000 | 3080000 | 0 | 0 | 0%
3.9 | Construction of Stone Masonry drain (Outlet) / Gabions | m3 | 45.6 | 75073.6429 | 3423358.1151 | 0 | 0 | 0%
3.1 | Plain Concrete | m3 | 1.44 | 250000 | 360000 | 0 | 0 | 0%
3.11 | RCC concrete | m3 | 13.6 | 450000 | 6120000 | 0 | 0 | 0%
3.12 | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | 1944 | 3500 | 6804000 | 0 | 0 | 0%
3.13 | Restoration of the road wearing course with selected materials | m3 | 1400 | 13989 | 19584600 | 0 | 0 | 0%
3.14 | Construction of Stone Masonry drain | m3 | 570 | 75073.6429 | 42791976.4387 | 0 | 0 | 0%
3.15 | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | 1166.4 | 3500 | 4082400 | 0 | 0 | 0%
3.16 | Supply and Installation of the Pipe culvert ɸ 100 | m | 8 | 250000 | 2000000 | 0 | 0 | 0%
3.17 | Ordinary cutting (to extend the CW_ width) hauling and final Disposal | m3 | 2400 | 5128 | 12307200 | 0 | 0 | 0%
3.18 | Construction of the outlet (Stone Masonry Drain / Gabions) | m3 | 28.5 | 75073.6429 | 2139598.8219 | 0 | 0 | 0%
3.19 | Supply and Construction of Gabions | m3 | 5 | 80146.1863 | 400730.9316 | 0 | 0 | 0%
3.2 | Supply and installation of beacons | m3 | 12 | 25000 | 300000 | 0 | 0 | 0%
3.21 | Wood lumber (squired) | m | 15 | 50000 | 750000 | 0 | 0 | 0%
3.22 | Construction of Stone Masonry (Head wall, retaining wall) | m3 | 9 | 75073.6429 | 675662.7859 | 0 | 0 | 0%
| S/total |  |  |  | 187711802.8251
4 | Nyabimata_ Muganza
4.1 | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | 4500 | 3500 | 15750000 | 4250 | 14875000 | 94.44%
4.2 | Restoration of the road wearing course with selected materials | m3 | 420 | 13989 | 5875380 | 0 | 0 | 0%
| S/total |  |  |  | 21625380 |  | 14875000
5 | Giswi- Uwinteko- Shili
5.1 | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | 980 | 3500 | 3430000 | 980 | 3430000 | 100%
5.2 | Restoration of the road wearing course with selected materials | m3 | 63 | 13989 | 881307 | 0 | 0 | 0%
| S/total |  |  |  | 4311307 |  | 3430000
6 | Kibeho-Kivu TP
6.1 | Supply and Installation of the Pipe culvert ɸ 100 | m | 16 | 250000 | 4000000 | 16 | 4000000 | 100%
6.2 | Construction of the outlet (Stone Masonry Drain / Gabions) | m3 | 14.25 | 75073.6429 | 1069799.411 | 14.25 | 1069799.411 | 100%
6.3 | Plain Concrete | m3 | 0.45 | 250000 | 112500 | 0.45 | 112500 | 100%
6.4 | RCC concrete | m3 | 4.25 | 450000 | 1912500 | 4.25 | 1912500 | 100%
6.5 | Removal of landslides, debris and sediments_ including hauling and final Disposal | m3 | 1512 | 3500 | 5292000 | 1512 | 5292000 | 100%
6.6 | Restoration of the road wearing course with selected materials | m3 | 70 | 13989 | 979230 | 0 | 0 | 0%
6.7 | Ordinary cutting (to extend the CW_ width) hauling and final Disposal | m3 | 750 | 5128 | 3846000 | 750 | 3846000 | 100%
6.8 | Construction of Stone Masonry drain | m3 | 28.5 | 75073.6429 | 2139598.8219 | 28.5 | 2139598.8219 | 100%
| S/total |  |  |  | 19351628.2329 |  | 18372398.2329
| General Total( Withhold Tax exclusive) |  |  |  | 278510337.844 |  | 52327398.2329 | 18.79%
| Withhold Tax |  |  |  | 49148883.1489 |  | 9234246.747
| General Total( Withhold Tax inclusive) |  |  |  | 327659220.9929 |  | 61561644.9799
| DONE BY: |  |  |  | VERIFIED AND APPROVED BY:
| ENGR BDE |  |  |  | RTDA
| Maj R RUDAKUBANA |  |  |  | Innocent HAGENIMA
| P/Coordinator |  |  |  | Project Engineer

## NYANZA REVISED
Progress for Emergency maintenance works for damaged road spots on NR6 in Nyanza District.
S/No | ITEM DESCRIPTION | UNIT | QTY | RATE | AMOUNT | EXEC QTY | EXEC AMT | PROGR%
1 | Site installation
1.1 | Site Installation and Withdraw | LS | 1 | 3500000 | 3500000 | 0.9 | 3150000 | 90%
1.2 | Topography (Before, During and After Works) | LS | 1 | 500000 | 500000 | 0.9 | 450000 | 90%
| S/Total |  |  |  | 4000000 |  | 3600000
2 | Preparatory Works
2.1 | Clearing, Cleaning and stripping topsoil | m2 | 280 | 1417.0915 | 396785.62 | 280 | 396785.62 | 100%
2.2 | Demolition & removal of damaged head wall and wing wall protection in gabions / stone masonry | m3 | 70.5 | 5000 | 352500 | 70.5 | 352500 | 100%
2.3 | Excavation and removal of failed material (layers) from the road section; drain and culverts ( outlet & inlet) | m3 | 356 | 5128 | 1825568 | 356 | 1825568 | 100%
| S/Total |  |  |  | 2574853.62 |  | 2574853.62
3 | Pipe Culvert and road section
3.1 | Construction of a new head and wing walls in stonemasonry | m3 | 33 | 75073.6429 | 2477430.2149 | 33 | 2477430.2149 | 100%
3.2 | Back fill with selected materials to restore the affected road layers | m3 | 306 | 13989 | 4280634 | 306 | 4280634 | 100%
3.3 | Supply and installation of pipe culverts ɸ80 | m | 8 | 220000 | 1760000 | 8 | 1760000 | 100%
3.4 | Supply and installation of pipe culverts ɸ100 | m | 8 | 250000 | 2000000 | 0 | 0 | 0%
3.5 | Onbed RCC slab to protect the outlet of the culvert | m3 | 4.725 | 450000 | 2126250 | 2.5 | 1125000 | 52.91%
3.6 | Supply and installation of gabions | m3 | 4 | 80146.1863 | 320584.7452 |  | 0 | 0%
3.7 | Plain concrete | m3 | 3 | 250000 | 750000 | 3 | 750000 | 100%
3.8 | Reinfiirced concrere (RCC) | m3 | 0.7 | 450000 | 315000 | 0 | 0 | 0%
3.9 | Stone masonry wall | m3 | 5.1 | 75073.6429 | 382875.5787 | 5.1 | 382875.5787 | 100%
| S/Total |  |  |  | 14412774.5388 |  | 10775939.7935
4 | Drain
4.1 | Construction of stonemasonry drain and manhole | m3 | 75.6 | 75073.6429 | 5675567.4013 | 75.6 | 5675567.4013 | 100%
4.2 | Installation of Drift | m | 9 | 21000 | 189000 | 0 | 0 | 0%
4.3 | Readjust the drain to the main outlet through existing (timber) culvert. | m | 8 | 21000 | 168000 | 8 | 168000 | 100%
| S/Total |  |  |  | 6032567.4013 |  | 5843567.4013
5 | Safety features
5.1 | RCC_Beacons | Pce | 32 | 25000 | 800000 | 32 | 800000 | 100%
| S/Total |  |  |  | 800000 |  | 800000
| General Total( Withhold Tax exclusive) |  |  |  | 27820195.5601 |  | 23594360.8149 | 84.81%
| Withhold Tax |  |  |  | 4909446.2753 |  | 4163710.732
| General Total( Withhold Tax inclusive) |  |  |  | 32729641.8355 |  | 27758071.5469
| DONE BY: |  |  |  | VERIFIED AND APPROVED BY:
| ENGR BDE |  |  |  | RTDA
| Maj R RUDAKUBANA |  |  |  | Eng Innocent HAGENIMA
| P/Coordinator |  |  |  | Project Engineer